How to Apply for and Manage

your Engagement Initiative

Table of Contents

- Welcome 	3

About this guide     	3

What is Facility Engagement?    	3

About the BC Cancer Medical Staff Engagement Society (MSES)    	4

Who are we and how to contact MSES   	4

Website links	4

- How to apply for Engagement Initiative Funds 	5

Project Criteria     	5

Application process     	7

Letter of Intent Form     	8

Full Application Form    	9

- How to Manage your Engagement Initiative 	11

Executing the budget    	11

How to access your funds 	11

Facility Engagement Management System (FEMS)    	11

Billing for Goods and Services   	14

Eligible Expenses 	14

FEMS Instructions

Before you start FEMS Registration Checklist    	14

Register for FEMS    	15

Register for FEMS using the mobile app 	16

Register for VersaPay (EFT payments)    	17

How to submit a claim in FEMS       	18

Reporting requirements  	19

Interim Report	20

Final Report  	21

Welcome!

On behalf of the BC Cancer Medical Staff Engagement Society we thank you for your interest in proposing and leading an engagement project. This guide is intended to provide information about:

- Facility Engagement and MSES

- Who the MSES team is and who to contact for help

- How to submit a project proposal

  - Funding criteria

  - Application forms

- Managing your project

  - How to access your funds

  - Registering for Facility Engagement Management System (FEMS)

  - How to process project expenses

  - How to claim physician sessional time

  - Reporting requirements

What is Facility Engagement?

- Facility Engagement is a provincial initiative that aims to improve communication, relationships and collaboration between health authorities and hospital-based physicians in BC, to benefit their work environment and patient care.

- Facility Engagement is part of the Physician Master Agreement; each Health Authority has committed through a Memorandum of Understanding to support greater engagement and collaboration with physicians.

- This is a first-time ever, formal opportunity for physicians, site administrators, and

the health authority to clarify and strengthen relationships and collaboration, and increase meaningful physician involvement in decision-making.

- Funding is governed by the Specialist Services Committee (SSC) and administered by the Facility Engagement Provincial Office at Doctors of BC.

- This funding supports:

  - Maintenance of a physician society, governance structure, including a Working Group and associated committees, administrative and support staff.

  - Projects and sessional payments for physicians involved.

- Through a medical staff engagement society’s formal structure and funding, physicians can voice their priorities, lead local activities tailored to their facility, and have a say in the future direction of their hospital.

- Physicians with privileges and who are members of the medical staff are welcome to participate - including specialists, general practitioners, alternatively paid physicians and other medical staff as determined by the MSA.

BC Cancer Medical Staff Engagement Society (MSES)

The BC Cancer MSES Working Group (WG) is a representative body for all physicians, dentists and nurse practitioners with privileges at BC Cancer Regional Centres. This includes physicians from discipline specific associations, physicians and dentists from disciplines without association status, nurse practitioners and regional representatives of the medical and dental staff of all the regional centres. The WG will represent the BC Cancer medical staff and liaise with BC Cancer and PHSA leadership to improve engagement on matters of importance to medical staff and patients. It is developing decision-making and funding structures to ensure effective representation and participation of all BC Cancer medical staff.  These structures, along with funding and support provided through the Memorandum of Understanding on Regional and Local Engagement, will:

- Support medical/dental staff engagement by providing a forum for the BC Cancer staff to express their views;

- Prioritize views and issues, and bring these to the attention of BC Cancer and PHSA leadership;

- Engage and collaborate with PHSA administration, BC Cancer executive leadership and physician leaders;

- Liaise with BC Cancer medical staff regarding issues of concern raised by the BC Cancer and PHSA administration.

BC Cancer MSES Board of Directors 2018/2019:

- Dr. Tamara Shenkier, President

- Dr. Paris-Ann Ingledew, Vice President

- Dr. Andrew McFadden, Treasurer-Secretary

- Dr. Dean Kolodziejczyk, Director-at-Large

BC Cancer MSES Committee Chairs 2018/2019:

- Engagement Initiative Committee: Dr. Sharlene Gill

- Communications Committee: Dr. Sally Smith, Dr. Jeffrey Sulpher

- CST Committee: Dr. Eric Tran, Dr. Bernie Eigl

- Wellness Committee: Dr. Mira Keyes

BC Cancer MSES Administrative Team:

- Dr. Dan Le, Managing Director

- Jennifer Barr, Project Manager, Engagement Initiatives

- Pam Whitworth, Communications Consultant

- Pauline Lee, Administrative Assistant

- Janice Wortman, Administrative Assistant

How to Contact MSES:

All enquires should be directed to bccamses@facilityengagement.ca.

Important Links:

BC Cancer Medical Staff Engagement Society (MSES): www.bccamses.com

Facility Engagement Management System (FEMS): https://fems.facilityengagement.ca/

Provincial Facility Engagement Resources: www.FacilityEngagement.ca

Specialist Services Committee: www.sscbc.ca

2. How to apply for Engagement Initiative Funds:

The BC Cancer MSES Engagement Initiatives Committee seeks your ideas for innovative ways to build physician engagement at BC Cancer.  By engagement, we mean physicians should perceive as a consequence of this endeavour, an increased sense that their input into BC Cancer direction matters and enhances mastery of their ability to contribute to patient care and their work environment.

Project Criteria:

- Strategic Priorities: 
Your proposal must address one or more of the MSES Strategic Priorities:

- To provide opportunities for communication between BC Cancer medical staff (across disciplines and across regional centres).

- To foster enhanced communication and collaboration between BC Cancer & PHSA leadership.

- To lead collaboration across "silos" to address inefficiencies and improve clinical work flow and indirect patient care.

- To promote medical staff wellness.

- New and emerging priorities may also be announced as needed by the BC Cancer MSES Board of Directors.

- General Criteria:

Proposals will be further reviewed based on the following criteria:

- Patient Care Quality

  - Will positively impact one or more of the following aspects of patient care:

    - Safety

    - Effectiveness

    - Timeliness

    - Improve efficiency and/or clinical workflow

- Implementation

  - Ease of implementing solution with respect to administrative and operational requirements

- Impact

  - Breadth of impact across multiple disciplines and regions

- MSES Membership:

# The Project Lead must be a member of BC Cancer MSES (any BC Cancer-affiliated physician, dentist, or nurse practitioner)

- Duration:

- Project duration must be for one year or less and funding must be expended within one year from the time of approval of funding.

- Generally no extension of funds will be granted beyond the funding end date.

- The completed application must be received by the submission deadline.

- Executive Sponsor:

In order to optimize stakeholder alignment, proposals that proceed to Stage 2 require a named sponsor from BC Cancer leadership (at level of Regional Medical Director or higher).

- Evaluating Success:

Project aims and methodology must be able to demonstrate measurable, achievable outcomes. The MSES Project Manager is available to help determine appropriate goals and how to measure your results.

- Budget Planning:

Projects may be within a smaller budget (less than $5000), medium budget ($5,000 - $10,000) or a larger budget (between $10,000 to $15,000).  If you reach Stage 2 of the application process, be prepared to provide detail for all aspects of your project:

Sessional Time

Salaried physicians, dentists and nurse practitioners are entitled to sessional reimbursement for time spent on their project outside of regular BC Cancer hours (8.30am to 5 pm) and outside the terms of their contracted role with BC Cancer.  Expenditures for sessional time must be accounted for within project budgets.

Allied health care workers

You are encouraged to include allied partners in your project plans as collaborators, team members, or for staff support (see Project Support below). If they are participating in a context outside of their salaried role they may be paid for their participation at their rate, provided their work is outside their normal working hours.

Project support

Project plans can include budget for hiring support staff such as administrative support, project coordination and management, research assistance, data analysis, medical writing, event planning, group and event facilitation.

Project Leads may make an arrangement with staff known to them in BC Cancer to provide assistance with their project. If the work does not fall under their existing contractual duties, BC Cancer staff may be paid for MSES project work provided they work outside of their regular hours at BC Cancer. The MSES Project Manager may be able to assist in providing support or recommending consultants with these skills.

- Funding Exclusions

Facility Engagement funding cannot be used for:

  - Clinically focused continuing medical education

  - Compensation for direct patient care

  - Purchase of real estate and vehicles

  - Purchase of clinical equipment

  - Donations to charities or political parties

  - Meeting attendance that is presently required as part of maintaining privileges

  - To purchase alcohol

  - To address a funding gap that is the responsibility of another stakeholder, such as the health authority.

Application Process:

Dates for call for proposals are announced by email through the MSES e-bulletin.

Proposals are considered in two stages:

Stage 1 	Letter of Intent

Brief 500 word description of your aim, how this will be achieved, which MSES strategic priorities are addressed, how will this project improve and/or support physician engagement, anticipated risks and a budget estimate (small, medium or large). Please see Letter of Intent Form below.

Stage 2 	Complete Application

If approved you will be asked to complete a more detailed description for final approval. Please see Full Application Form below.

Engagement Initiative Proposal:  LETTER OF INTENT

Proposal Title:

Name of Principal Applicant:

Email:

BC Cancer Centre:

Department(s):

Name of BC Cancer sponsor (at level of Regional Medical Director or higher):

Name(s) of co-applicants (if any):

In less than 500 words, please describe:

Aim(s) of proposal

How will the aim(s) be achieved?

Which MSES strategic priorities are addressed by this proposal?

How will this project improve and/or support physician engagement?

Risks/Challenges

Anticipated Budget:

___< $5,000                              ___$5,000 - $10,000                         ___$10,000 - $15,000

Please submit by the email to bccamses@facilityengagement.ca

Engagement Initiative FULL APPLICATION  (TO BE COMPLETED ONLY AFTER YOUR LOI IS APPROVED)

PROPOSAL TITLE:

Name of Principal Applicant:

Email:

BC Cancer Centre:

Department(s):

Support Staff (if applicable):

BC Cancer Leadership Sponsor:

Co-Applicants: (Name; Position; Affiliation)

DESCRIPTION: (max 2 pages for this section)

Objective(s):

What are you aiming to accomplish?

What problem, situation or need will this address?

Why is this activity important?

Outcomes and Impact:

What are the outcomes you are hoping to achieve?

How will success be measured?

How will this activity improve engagement?

Methodology:

How do you intend to achieve your aim?

Planned milestones and timeline:

What are the anticipated milestones that will mark your progress (and timing)?

Stakeholders:

Identify your Health Authority project partners/collaborators

Identify all stakeholders who will be impacted by the project outcome(s)

How do you intend to involve BC Cancer leadership, the health authority and other clinical partners in the initiative?

Alignment:

Which MSES strategic priorities are addressed by this proposal?

Related Projects:

Are there any related projects within BC Cancer and/or PHSA that may impact this project? Have you explored possible collaboration or partnerships with other similar initiatives, or are you willing to?

Risks/challenges:

What risks have you identified that could impede the success of your initiative? How can these risks be mitigated?

Dissemination and Sustainability:

How will the results of this engagement activity be disseminated? Once complete how will the impact of the activity be sustained?

Budget Planning and Details:

The Excel “Budget Builder” will assist you in determining details and costs of your budget request. The Budget Builder is available on the MSES website. (Note the Explanatory Notes and Sample Budget Tabs. Please itemize your budget details or attach your completed Budget).

Total Budget Requested:  $____________

Please submit your full application with budget details by email to

bccamses@facilityengagement.ca

3. Managing Your Project

Executing the budget

Your budget has been approved for the project as specified in your application; funds cannot be used for other purposes without the written approval of the Engagement Initiative Committee Chair, a member of the BC Cancer MSES Board of Directors, or the BC Cancer MSES Managing Director.

All funds must be used within one year as per the dates specified in your approval notice.

Accessing your funds

All MSES funds are managed by the online Facility Engagement Management System (FEMS). Once you have received your Letter of Approval for your project, your project will have been entered into FEMS and will appear as a designated “Engagement Activity” with your budget amount. Funds are then accessible for reimbursement for expenses, for claiming sessional time (if applicable) by you and other medical staff on your team, and for billing for other costs such as staff support and supplies. FEMS keeps track of funds and provides MSES directors, administrators and our funders with reports and records. In addition FEMS offers opportunities throughout your project involvement to provide input into the UBC Evaluation. (For information about the UBC Provincial Evaluation see www.facilityengagement.ca).

Facility Engagement Management System (FEMS)

In order to activate FEMS for your project, you and your team of physicians who will be making claims (expense claims or sessional claims) must register for both FEMS and VersaPay.  VersaPay is the Canadian-hosted version of Pay Pal for secure direct-to-your bank deposits. An MSES executive will review and approve all claims before they are paid out either through FEMS or by invoice. Further detail may be required.  Please see pages 14 to 18 for detailed FEMS instructions. Once you have registered you and other physician team members must email bccamses@facilityengagement.ca to let us know you have registered and what initiative you are involved in.  MSES administrative support will then add new registrants to their assigned Engagement Activity in FEMS enabling you and your team to make claims.

FEMS support

If you have trouble registering or have other FEMS related questions, please email bccamses@facilityengagement.ca or femssupport@doctorsofbc.ca. There is a FEMS helpline at 604 638 4869 available between 9 and 4 weekdays.

Claiming Sessional Time

BC Cancer salaried physicians and dentists are entitled to reimbursement at their sessional rate for time spent on their project or as a project team member outside of regular BC Cancer hours (8.30am to 5 pm) and outside the terms of their contracted role with BC Cancer. This time is to be claimed through FEMS; a record must be kept of date, times, and amount of time spent and a list of tasks and activities achieved. You must make your claim within 3 months.

Submitting Expense Claims for Reimbursement

After you have paid an expense, please keep your receipts.  You will need to upload your receipts to your Engagement Activity on FEMS. You will then be reimbursed via Versapay.

Billing for good and services

Large Expenses

Large expenses (generally >$1000) can be paid upfront by the Project Lead and reimbursed via FEMS,

or an invoice can be submitted and MSES will then pay the invoice directly via cheque.

The invoice should specify the project name and individual or company name, address, dates, itemized services or goods provided and if applicable, hours worked, and activities performed for each hour. The invoice is to be submitted directly to bccamses@facilityengagement.ca and will be paid by cheque, and mailed to the individual or company; the amount will be reported in your project tally in FEMS.  Please check with bccamses@facilityengagement.ca or the Project Manager if you need any clarification.

Contracted goods or services

A written contract may be necessary if it is for an independent service provider (e.g. a part-time employment contract or supplier) over a substantial period of time (such as more than 6 months). Please check with MSES for clarification if you have questions, and for a contract template. If you are entering into a contract with an individual/organization please prepare the contract and then submit it to bccamses@facilityengagement.ca for review and signature.  An MSES Director must sign the contract on behalf of the Society.

PHSA/BC Cancer invoices

Staff back-fill and other services (as per your approved project plans) provided by a unit or department of BC Cancer or PHSA can be reimbursed by preparing an invoice specifying the details as above and submitting this to bccamses@facilityengagement.ca.

Eligible Expenses

Reasonable expenses incurred while participating in approved engagement projects may be claimed by Project Leads, Project Team members and participants including:

Accommodation

- Maximum of $220 per night before tax for accommodation

- Accommodation expenses are not an eligible expense where the conference or meeting is fewer than 50km from the claimant’s personal residence

Meals

- Breakfasts, lunch and/or dinner expenses while attending an event, or spent during travel to and from the event

- Legible itemized receipts are required to be submitted with the claim.

- Meal expenses will be capped at $100 per day.

- Recommended rates of breakfast $20, lunch $30, dinner $50

- Alcohol will not be reimbursed

- If a meal is provided without charge, no claim for that meal can be made.

Travel

- Costs for the most reasonable and economical route to attendance;

- Travel expenses will be reimbursed for the most expeditious route of travel (economy flights only; upgrades to be paid by traveler; booking well in advance)

- Reimbursement will be made where one-way travel from the claimant’s personal residence exceeds 50 km.

- Vehicle expenses will be reimbursed at $ 0.55/kilometer for private vehicle mileage incurred if one-way travel exceeds 50 km; requirement to specify number of kms with claim

- Mileage expenses must not exceed airfare for the same travel

- Taxis and car rentals will be reimbursed in addition to airfare when required

- Parking costs will be reimbursed.

Travel Time

- Reasonable travel time may be paid at the sessional rate for time outside of BC Cancer regular hours using the most expeditious route of travel. Exceptions to this policy will be given individual consideration.

Reporting:

The following written reports are required:

- Interim Report (6 months point)

- Final Report (upon completion of 12 months project term)

Part or all of your report may be shared with your Executive Sponsor, the Facility Engagement Provincial Office, the Specialist Services Committee, the UBC Facility Engagement Evaluation Team and others interested in our progress and achievements. If time permits, you may be invited to present on your initiatives project at the BCCA MSES AGM or other opportunities. You will be prompted to submit these reports at the appropriate time. Please see Report Forms below (Pages 20 and 21).

Thank you for your leadership and contribution in improving engagement at BC Cancer.

Engagement Initiative Interim Report

Submission Due Date:

Project Title:

Project Lead:

Executive Sponsor:

- PROGRESS:

Briefly describe your activity to date.

- MILESTONES ACHIEVED:

- CHALLENGES:

Describe any unexpected challenges or barriers you have experienced in implementing your plans.

- BUDGET:

State amount of expenses claimed to date and if you will require the full amount of your approved budget.

Engagement Initiative Final Report

Submission Due Date:

Project Title:

Physician Lead:

Executive sponsor:

1. Results: Please briefly describe progress, milestones achieved, measurable outcomes and overall impact of your project. Kindly limit your description to a maximum of 1000 words for this section; and append any relevant reports produced for the project.

Progress:

Milestones achieved:

Outcomes:

Impact:

2. Challenges: Please describe any challenges or unexpected barriers you experienced in implementing your plans.

3. Next steps: What further actions will you will be taking to disseminate your findings and/or to promote the sustainability of this initiative?

4. Budget: If your project funds are not fully expended, please provide an estimate of any outstanding expenses yet to be charged to your approved budget.

5. Change: Please describe a key change or improvement that occurred in relationships, communication and/or collaboration among physicians and medical staff, or between physicians and site administration, and/or the health authority.

6. Lessons learned: Please describe a key lesson or lessons learned or a successful strategy that you wish to share and that may benefit others doing these types of projects.